## Timeline
Project timeline DWH data retention – Weekly
ID | Aktivitas | Mulai | Selesai | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25
1 | Tahap 1 – Dokumentasi (BRD & FSD) | 2026-10-26 | 2026-11-13 | 1 | 1 | 1
1.1 | Kick-off proyek dan identifikasi stakeholder | 2026-10-26 | 2026-10-26 | 1
1.2 | Pengumpulan kebutuhan bisnis dan teknis | 2026-10-27 | 2026-10-30 | 1
1.3 | Penyusunan BRD (Business Requirements Document) | 2026-10-29 | 2026-11-04 | 1 | 1
1.4 | Review, revisi, dan persetujuan BRD | 2026-11-05 | 2026-11-06 |  | 1
1.5 | Penyusunan FSD (Functional Specification Document) | 2026-11-05 | 2026-11-11 |  | 1 | 1
1.6 | Review, revisi, dan persetujuan FSD | 2026-11-12 | 2026-11-13 |  |  | 1
2 | Tahap 2 – Pengembangan (build, SIT, uji performa) | 2026-11-02 | 2026-12-18 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
2.1 | Kesiapan infrastruktur oleh Customer: Integration Runtime, jaringan, storage container, akses database | 2026-11-02 | 2026-11-13 |  | 1 | 1
2.2 | Analisis tabel DWH dan technical assessment (kategori ukuran tabel, metode Initial Cut-off, objek dependen, indeks) | 2026-11-09 | 2026-11-20 |  |  | 1 | 1
2.3 | Build objek database: tabel konfigurasi, tabel parameter, tabel log, dan stored procedure retensi | 2026-11-16 | 2026-11-27 |  |  |  | 1 | 1
2.4 | Build pipeline ADF (Initial Cut-off Run, Daily Routine, arsip Parquet, penghapusan arsip kedaluwarsa) dan schedule trigger | 2026-11-16 | 2026-12-02 |  |  |  | 1 | 1 | 1
2.5 | Unit test, code review, dan uji integrasi di DEV | 2026-11-30 | 2026-12-04 | [5 empty] | 1
2.6 | System Integration Testing (termasuk skenario gagal, rerun, resume) | 2026-12-07 | 2026-12-11 | [6 empty] | 1
2.7 | Uji performa terhadap baseline; tuning batch size/jeda; estimasi durasi Initial Cut-off per tabel | 2026-12-07 | 2026-12-11 | [6 empty] | 1
2.8 | Persiapan UAT: skenario uji, data uji, akses pengguna | 2026-12-07 | 2026-12-11 | [6 empty] | 1
2.9 | Dokumentasi operasional: desain, konfigurasi, setup, panduan operasional | 2026-11-30 | 2026-12-18 | [5 empty] | 1 | 1 | 1
3 | Tahap 3 – User Acceptance Testing (UAT) | 2026-12-14 | 2026-12-18 | [7 empty] | 1
3.1 | Eksekusi UAT | 2026-12-14 | 2026-12-16 | [7 empty] | 1
3.2 | Tuning dan uji ulang | 2026-12-16 | 2026-12-17 | [7 empty] | 1
3.3 | Sign-off UAT | 2026-12-18 | 2026-12-18 | [7 empty] | 1
4 | Tahap 4 – Implementasi (deployment dan Initial Cut-off Run) | 2026-12-14 | 2026-12-25 | [7 empty] | 1 | 1
4.1 | Persiapan deployment: runbook, rencana rollback, jadwal Initial Cut-off | 2026-12-14 | 2026-12-18 | [7 empty] | 1
4.2 | Keputusan Go/No-Go | 2026-12-21 | 2026-12-21 | [8 empty] | 1
4.3 | Deployment ke production (trigger Daily Routine belum aktif); input konfigurasi oleh pengguna Customer | 2026-12-21 | 2026-12-21 | [8 empty] | 1
4.4 | Initial Cut-off Run – tabel kecil dan menengah (batch delete) | 2026-12-21 | 2026-12-23 | [8 empty] | 1
4.5 | Initial Cut-off Run – tabel besar (table rebuild) | 2026-12-23 | 2026-12-24 | [8 empty] | 1
4.6 | Aktivasi Daily Routine – sehari setelah Initial Cut-off terakhir selesai | 2026-12-25 | 2026-12-25 | [8 empty] | 1
5 | Tahap 5 – Hypercare (monitoring dan support) selama 1 bulan | 2026-12-26 | 2027-01-25 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1
5.1 | Monitoring intensif: hasil Initial Cut-off, eksekusi awal Daily Routine, review log harian dan rekonsiliasi | 2026-12-26 | 2027-01-08 | [8 empty] | 1 | 1 | 1
5.2 | Knowledge transfer ke Tim Operasional / Support | 2027-01-04 | 2027-01-15 | [10 empty] | 1 | 1
5.3 | Support hypercare reguler: penyelesaian isu, tuning batch, observasi akhir bulan | 2027-01-09 | 2027-01-25 | [10 empty] | 1 | 1 | 1 | 1
5.4 | Penutupan hypercare, serah terima, dan penutupan proyek | 2027-01-21 | 2027-01-25 | [12 empty] | 1 | 1
Minggu berjalan (hari ini) ditandai garis merah.

## List Table
List Table
Table | Group | Function
ret.RetentionConfig | Configuration | Central configuration: one row per table under retention.
ret.RetentionTableStatus | Configuration | Initial Cut-off status, completion date and blocking flags per table.
ret.RetentionParameter | Configuration | Global parameters: batch size, pause, IC window, retries, Daily Routine start date.
ret.RetentionRunLog | Logging | One row per pipeline execution.
ret.RetentionTableLog | Logging | One row per table per execution with all attributes and resume control.
ret.RetentionArchiveDate | Logging | Per business date snapshot and export result; basis of row-count validation.
ret.RetentionStepLog | Logging | Detailed step trail for troubleshooting.
ret.RetentionTableLock | Control | Prevents two runs from processing the same table.
ret.RetentionErrorCode | Reference | Reference list of error and warning codes.

## RetentionConfig
ret.RetentionConfig
Column | Data type | Null | Default | Description
TableConfigId | INT IDENTITY | No |  | Surrogate key referenced by status, lock and log tables.
SchemaName | SYSNAME | No |  | Schema of the table under retention, e.g. BOS.
TableName | SYSNAME | No |  | Table under retention, e.g. JTI_SD_BrandDistDetail.
RetentionColumn | SYSNAME | No |  | Business date column. Must be date, datetime, datetime2 or smalldatetime and contain no NULL values; checked at run time.
DwhRetentionYears | SMALLINT | No | 3 | Years kept in the DWH.
BlobRetentionYears | SMALLINT | No | 5 | Years kept as Parquet files in Azure Blob Storage after the DWH period. Total retention is not stored: it is calculated as DwhRetentionYears + BlobRetentionYears (3 + 5 = 8).
BlobPath | NVARCHAR(400) | No |  | Table root folder inside the archive container. Unique; no leading or trailing slash.
InitialCutoffMethod | VARCHAR(20) | No |  | Initial Cut-off Run method: BATCH_DELETE or TABLE_REBUILD.
IsActive | BIT | No | 1 | 1 = table is processed; 0 = excluded from process.
SizeCategory | VARCHAR(10) | No |  | SMALL, MEDIUM or LARGE from the technical assessment.
CreatedBy | NVARCHAR(128) | No |  | Login that created the row.
CreatedAt | DATETIME2(3) | No | Now (UTC+7) | Creation time (UTC+7).
ModifiedBy | NVARCHAR(128) | Yes |  | Login of the last change; set by trigger.
ModifiedAt | DATETIME2(3) | Yes |  | Time of the last change (UTC+7); set by trigger.

## RetentionTableStatus
ret.RetentionTableStatus
Column | Data type | Null | Default | Description
TableConfigId | INT | No |  | Configuration entry (primary key and foreign key).
InitialCutoffStatus | VARCHAR(10) | No | PENDING | PENDING, RUNNING, FAILED, STOPPED or COMPLETED.
InitialCutoffCompletionDate | DATE | Yes |  | UTC+7 calendar date on which the Initial Cut-off Run completed. The Daily Routine includes the table only when run date > this date.
LastInitialCutoffRunId | BIGINT | Yes |  | Last run that executed the Initial Cut-off Run for the table.
HasOrphanFiles | BIT | No | 0 | 1 = archive files of a failed run could not be removed. Blocks processing.
OrphanFilesRunId | BIGINT | Yes |  | Run that left the orphan files.
HasIntegrityIssue | BIT | No | 0 | 1 = integrity problem detected. Blocks processing.
IntegrityIssueRunId | BIGINT | Yes |  | Run that raised the integrity flag.
HasReconciliationWarning | BIT | No | 0 | 1 = deleted total differed from validated total. Informational, not blocking.
ReconciliationWarningRunId | BIGINT | Yes |  | Run that raised the warning.
FlagComment | NVARCHAR(400) | Yes |  | Reason for the last flag change, including operator comments when cleared.
ModifiedBy | NVARCHAR(128) | No |  | Login of the last change.
ModifiedAt | DATETIME2(3) | No | Now (UTC+7) | Time of the last change (UTC+7).

## RetentionParameter
ret.RetentionParameter
Column | Data type | Null | Default | Description
ParameterSetId | TINYINT | No |  | Global parameter ID
BatchSize | INT | No | 10000 | Maximum rows per delete batch.
BatchPauseSeconds | INT | No | 3 | Pause between delete batches in seconds.
IcWindowStart | TIME(0) | No | 21:00 | Start of the Initial Cut-off Run window. Default 09:00 PM UTC+7.
IcWindowEnd | TIME(0) | No | 5:00 | End of the Initial Cut-off Run window. Default 05:00 AM UTC+7.
DailyRoutineStartDate | DATE | Yes |  | First run date on which the Daily Routine selects tables. Set by usp_ActivateDailyRoutine.
DeleteRetryCount | TINYINT | Yes |  | Retries per delete batch on deadlock (1205) or lock timeout (1222). NULL = no retry.
DeleteLockTimeoutMs | INT | Yes |  | LOCK_TIMEOUT for delete batches in milliseconds. NULL = wait indefinitely.
DailyNullCheckMode | VARCHAR(10) | No | FULL | FULL = count NULLs in the retention column every Daily Routine; METADATA = skip the data check for nullable columns.
KeepRebuildStagingTable | BIT | No | 1 | 1 = keep the staging table after a table rebuild until sign-off.
ArchiveContainer | NVARCHAR(63) | Yes | schema/table/year/month/ | Azure Blob Storage container of the archive.
ModifiedBy | NVARCHAR(128) | No |  | Login of the last change.
ModifiedAt | DATETIME2(3) | No | Now (UTC+7) | Time of the last change (UTC+7).

## RetentionRunLog
ret.RetentionRunLog
Column | Data type | Null | Default | Description
RunId | BIGINT IDENTITY | No |  | Unique execution identifier; also used in archive file names.
AdfPipelineRunId | UNIQUEIDENTIFIER | Yes |  | ADF pipeline run ID. Unique when present; makes usp_StartRun idempotent on ADF retries.
ProcessType | VARCHAR(20) | No |  | INITIAL_CUTOFF, DAILY_ROUTINE or VALIDATION.
RunDate | DATE | No |  | Run date in UTC+7, fixed for the whole run.
IsRunDateOverride | BIT | No | 0 | 1 = run date differs from the current UTC+7 date (manual rerun for an earlier date).
TriggerType | VARCHAR(10) | No |  | SCHEDULE or MANUAL.
TriggeredBy | NVARCHAR(256) | Yes |  | Operator identity for manual runs.
DowntimeReference | NVARCHAR(100) | Yes |  | Approved downtime reference; required for LARGE tables and TABLE_REBUILD.
StartTime | DATETIME2(3) | No | Now (UTC+7) | Run start (UTC+7).
EndTime | DATETIME2(3) | Yes |  | Run end (UTC+7); NULL while RUNNING.
Status | VARCHAR(25) | No | RUNNING | RUNNING, SUCCEEDED, COMPLETED_WITH_ERRORS or FAILED.
TablesSelected | INT | Yes |  | Tables selected for processing.
TablesSucceeded | INT | Yes |  | Tables ended SUCCEEDED or NODATA.
TablesFailed | INT | Yes |  | Tables ended FAILED or STOPPED.
TablesSkipped | INT | Yes |  | Tables skipped (not eligible or locked).
ErrorCode | VARCHAR(12) | Yes |  | Run-level error code, if any.
ErrorMessage | NVARCHAR(MAX) | Yes |  | Run-level error details.
IsClosedManually | BIT | No | 0 | 1 = closed by an operator with usp_AdminCloseStaleRun.
ClosedBy | NVARCHAR(128) | Yes |  | Operator who closed the run manually.
CloseComment | NVARCHAR(400) | Yes |  | Investigation comment entered by the operator.

## RetentionTableLog
ret.RetentionTableLog
Column | Data type | Null | Default | Description
TableLogId | BIGINT IDENTITY | No |  | Unique identifier of the table log.
RunId | BIGINT | No |  | Execution (FK to RetentionRunLog).
TableConfigId | INT | No |  | Configured table (FK to RetentionConfig).
ProcessType | VARCHAR(20) | No |  | Process type of the run.
RunDate | DATE | No |  | Run date, UTC+7.
DwhCutoffDate | DATE | Yes |  | Run date minus DWH retention.
ArchiveCutoffDate | DATE | Yes |  | Run date minus total retention.
MethodUsed | VARCHAR(20) | Yes |  | BATCH_DELETE or TABLE_REBUILD.
EligibleRows | BIGINT | Yes |  | Rows to remove from the DWH. Initial Cut-off Run: archived plus expired rows.
ArchivedSegmentRows | BIGINT | Yes |  | Initial Cut-off Run: rows from archive cut-off to the day before DWH cut-off.
ExpiredSegmentRows | BIGINT | Yes |  | Initial Cut-off Run: rows before the archive cut-off (deleted without archiving).
ExportDateCount | INT | Yes |  | Number of business dates to export.
RowsExported | BIGINT | Yes |  | Rows written to Parquet.
PreDeleteRecount | BIGINT | Yes |  | Recount of the validated range immediately before deletion.
RowsDeleted | BIGINT | Yes |  | Rows deleted from the DWH for this log's validated range.
ResumeRowsDeleted | BIGINT | Yes |  | Rows this run deleted for an earlier run's validated range (resume).
DeleteBatchCount | INT | Yes |  | Number of delete batches executed.
RebuildStagingTable | NVARCHAR(260) | Yes |  | Staging table of a table rebuild, if kept (DEC-08).
ArchiveFoldersDeleted | INT | Yes |  | Expired archive folders deleted.
ArchiveFilesDeleted | INT | Yes |  | Expired archive files deleted.
RetainedRowsBefore | BIGINT | Yes |  | Initial Cut-off Run: rows on or after the DWH cut-off before deletion.
RetainedRowsAfter | BIGINT | Yes |  | Initial Cut-off Run: same count after deletion.
IsValidated | BIT | No | 0 | 1 = archive validation passed; deletion of the range may proceed.
ValidatedRangeFrom | DATE | Yes |  | Inclusive lower bound of the validated range; NULL = unbounded.
ValidatedRangeTo | DATE | Yes |  | Exclusive upper bound of the validated range (= DWH cut-off date).
ValidatedRowCount | BIGINT | Yes |  | Rows expected to be deleted in the validated range.
DeleteStatus | VARCHAR(15) | No | NOT_STARTED | NOT_STARTED, IN_PROGRESS, COMPLETED, FAILED or NOT_REQUIRED. A validated range not COMPLETED is resumed by the next run.
ResumedByRunId | BIGINT | Yes |  | Run that completed an interrupted deletion of this range.
Status | VARCHAR(10) | No | RUNNING | RUNNING, SUCCEEDED, NODATA, FAILED, SKIPPED or STOPPED.
StartTime | DATETIME2(3) | No | Now (UTC+7) | Table processing start (UTC+7).
EndTime | DATETIME2(3) | Yes |  | Table processing end (UTC+7).
ErrorCode | VARCHAR(12) | Yes |  | First (non-warning) error code.
ErrorNumber | INT | Yes |  | SQL Server or ADF error number.
ErrorStep | VARCHAR(30) | Yes |  | Step in which the error occurred.
ErrorMessage | NVARCHAR(MAX) | Yes |  | Error details; later messages are appended.

## RetentionArchiveDate
ret.RetentionArchiveDate
Column | Data type | Null | Default | Description
TableLogId | BIGINT | No |  | Table log (FK).
BusinessDate | DATE | No |  | Business date of the exported rows.
RunId | BIGINT | No |  | Run that exported the date (FK).
TableConfigId | INT | No |  | Configured table (FK).
ExpectedRows | BIGINT | No |  | Rows counted in the DWH for this date before export (snapshot).
RowsRead | BIGINT | Yes |  | Rows read by the ADF Copy activity.
RowsWritten | BIGINT | Yes |  | Rows written to Parquet by the ADF Copy activity.
FileCount | INT | Yes |  | Parquet files written for the date.
FolderPath | NVARCHAR(1024) | No |  | <BlobPath>/business_date=yyyy-MM-dd.
FileName | NVARCHAR(400) | No |  | <schema>_<table>_<yyyyMMdd>_<RunId>.parquet; never overwritten.
ExportStatus | VARCHAR(10) | No | PENDING | PENDING, SUCCEEDED, FAILED, STOPPED, or REMOVED (files of a failed run deleted).
ValidationResult | VARCHAR(10) | Yes |  | PASSED or FAILED: ExpectedRows = RowsRead = RowsWritten.
ExportStartTime | DATETIME2(3) | Yes |  | Copy activity start (UTC+7), when supplied by ADF.
ExportEndTime | DATETIME2(3) | Yes |  | Time the result was recorded (UTC+7).
ErrorMessage | NVARCHAR(MAX) | Yes |  | Copy activity error, if any.

## RetentionStepLog
ret.RetentionStepLog
Column | Data type | Null | Default | Description
StepLogId | BIGINT IDENTITY | No |  | Unique identifier of the step record.
RunId | BIGINT | No |  | Execution (FK).
TableLogId | BIGINT | Yes |  | Table log; NULL for run-level steps.
TableConfigId | INT | Yes |  | Configured table; NULL for run-level steps.
StepCode | VARCHAR(30) | No |  | START_RUN, SELECT_TABLES, LOCK, VALIDATE, RESUME, COUNT, EXPORT, VALIDATE-ARCHIVE, RECOUNT, DELETE, REBUILD, POSTCHECK, CLEANUP, EXPIRE, END_TABLE, END_RUN or ADMIN.
ValidationCheckCode | VARCHAR(4) | Yes |  | V-01 to V-09 for a failed validation check.
BusinessDate | DATE | Yes |  | Business date for export steps.
ExpectedRows | BIGINT | Yes |  | Expected rows (snapshot).
RowsRead | BIGINT | Yes |  | Rows read (export).
RowsWritten | BIGINT | Yes |  | Rows written (export).
FilePath | NVARCHAR(2000) | Yes |  | File written or deleted.
FileCount | INT | Yes |  | Files written, deleted or removed.
BatchCount | INT | Yes |  | Delete batches executed.
RowsProcessed | BIGINT | Yes |  | Rows deleted, or folders deleted for EXPIRE.
ReferenceRunId | BIGINT | Yes |  | For RESUME: run that owns the resumed range.
Status | VARCHAR(10) | No | RUNNING | RUNNING, SUCCEEDED, FAILED, SKIPPED, STOPPED or WARNING.
StartTime | DATETIME2(3) | No | Now (UTC+7) | Step start (UTC+7).
EndTime | DATETIME2(3) | Yes |  | Step end (UTC+7).
Message | NVARCHAR(4000) | Yes |  | Informational or warning text.
ErrorCode | VARCHAR(12) | Yes |  | Error code of a failed step.
ErrorNumber | INT | Yes |  | SQL Server or ADF error number.
ErrorMessage | NVARCHAR(MAX) | Yes |  | Error details.

## RetentionTableLock
ret.RetentionTableLock
Column | Data type | Null | Default | Description
TableConfigId | INT | No |  | Locked table (primary key: one lock per table).
RunId | BIGINT | No |  | Run holding the lock.
ProcessType | VARCHAR(20) | No |  | Process type of the holding run.
AcquiredAt | DATETIME2(3) | No | Now (UTC+7) | Time the lock was acquired (UTC+7).
AcquiredBy | NVARCHAR(128) | No |  | Login that acquired the lock.

## RetentionErrorCode
ret.RetentionErrorCode
Column | Data type | Null | Default | Description
ErrorCode | VARCHAR(12) | No |  | Code in the format ERR-XXX-nn.
Category | NVARCHAR(50) | No |  | Error category.
Description | NVARCHAR(400) | No |  | Meaning of the code.
IsWarning | BIT | No | 0 | 1 = warning (non-blocking), 0 = error.

## Trigger and Functions
Triggers
Trigger | Event | Behaviour
ret.trg_RetentionConfig_AfterInsert | AFTER INSERT on RetentionConfig | Creates the RetentionTableStatus row with Initial Cut-off status PENDING, so that a new table is not processed by the Daily Routine before its own Initial Cut-off Run.
ret.trg_RetentionConfig_AfterUpdate | AFTER UPDATE on RetentionConfig | Sets ModifiedBy and ModifiedAt. Rejects changes to database, schema, table, retention column or blob path once the Initial Cut-off Run is RUNNING or COMPLETED, or any range of the table has been validated, because the archive would become inconsistent.
Functions
Function | Parameters | Returns | Purpose
ret.fn_NowUtc7 | (none) | DATETIME2(3) | Current date and time in UTC+7. Azure SQL Database runs in UTC, so GETDATE() is not used.
ret.fn_TodayUtc7 | (none) | DATE | Current date in UTC+7; default run date and Initial Cut-off completion date.
ret.fn_GetCutoffDates | @RunDate DATE, @DwhRetentionYears SMALLINT, @BlobRetentionYears SMALLINT | TABLE (TotalRetentionYears, DwhCutoffDate, ArchiveCutoffDate) | Total retention and cut-off dates : TotalRetentionYears = DWH + Blob years; DWH cut-off = run date - DWH years; archive cut-off = run date - (DWH + Blob) years. Example : run date 2026-10-27 with 3 + 5 years gives 8, 2023-10-27 and 2018-10-27. Single source of the formula for all procedures and for ADF.
ret.fn_IsWithinWindow | @Time TIME(0), @WindowStart TIME(0), @WindowEnd TIME(0) | BIT | 1 when a time is inside a window that may cross midnight, e.g. 09:pm - 05:00 AM.
ret.fn_ArchiveFolderPath | @BlobPath NVARCHAR(400), @BusinessDate DATE | NVARCHAR(1024) | Archive folder <BlobPath>/business_date=yyyy-MM-dd.
ret.fn_ArchiveFileName | @SchemaName SYSNAME, @TableName SYSNAME, @BusinessDate DATE, @RunId BIGINT | NVARCHAR(400) | Archive file name <schema>_<table>_<yyyyMMdd>_<RunId>.parquet.
ret.fn_DelayString | @Seconds INT | CHAR(8) | Converts seconds to hh:mm:ss for WAITFOR DELAY (pause between batches).